## Workplan
Central Florida Navy League Pickleball Tournament
# | Tasks | Description | Notes | Committee | Owner | Start | End | Status
1 | General Tournament
1.1 | Reserve facility | Reservation for facility | Call Clear One to lock in facility and dates | Operations | Brent | 2023-03-08 | 2023-03-08 | Complete
1.2 | Create Committees | Determine committees and sub-committees that will be required | In progress | NA | Brent | 2023-03-08 | 2023-04-01 | Complete
1.3 | Create Tournament name | Leverage Navy League for potential historical naming ideas | 1.Pickle for Patriots | Operations | Brent | 2023-03-08 | 2023-04-23 | Complete
1.4 | Add sign up functionality to website | Utilize same functionality used for luncheon sign ups |  | Operations | Brent | 2023-03-08 | 2023-04-24 | Complete
2 | Operations
2.1 | Determine registration fee | Determine the price per individual/team if a discount for Navy League members should be applied | $40-$50 per person | Operations | Brent | 2023-04-17 | 2023-04-18 | Complete
2.2 | Determine sign up process | Determine how individuals will sign up and register their team |  | Operations | Brent | 2023-03-08 | 2023-04-01 | Complete
2.3 | Finalize tournament structure | Determine the tournament structure (Double elimination, winners/losers bracket) | Decide on double elimination, age brackets, men's doubles v women's doubles | Operations | Brent | 2023-03-08 | 2023-04-01 | Complete
2.4 | Projector for tournament bracket | Determine if we can project the tournament bracket on to the wall | Project on wall or provide other means to view bracket update, update on tv? | Operations | TBD |  |  | Not Started
3 | Sponsorship
3.1 | Draft Sponsorship List | Initial list of companies to reach out to for sponsorship |  | Sponsorship |  | 2023-03-08 | 2023-04-01 | In Progress
3.2 | Generate tournament ideas for sponsorship | Ex) Sponsor for individual courts |  | Marketing/Sponsorship |  | 2023-03-08 | 2023-04-01 | Complete
4 | Marketing
4.1 | Create Tournament Graphic | Graphic for social media | 3/8/23 - Brent sent initial email to Lindsey with ideas | Marketing | Brent | 2023-03-08 | 2023-04-01 | Complete
4.2 | Receive quote for sponsorship banner | Reach out to POC that was used for WWLS race | Kirk or WWLS sponsor | Marketing | Brent/Berk | 2023-04-24 |  | In Progress
4.3 | Determine what winners receive | Decide on what tournament winners will receive | Diadem sports paddles | Operations/Marketing | Brent | 2023-04-24 | 2023-06-02 | Complete
4.3 | DJ for music/announcements | DJ for music/announcements | Reach out to Nate Wheeler | Marketing | Brent | 2023-04-24 | 2023-05-01 | Complete
4.3 | Drink Sponsor | Company to sponsor bar | Stephen Gould | Marketing | Berkley | 2023-04-24 |  | In Progress
5 | Misc
5.1 | Finalize announcer/MC | Announcer for event that can announce court assignments and provide fun atmostphere | Randy Fonatanez Dad | Marketing | TBD | TBD | TBD | TBD
5.2 | Determine refereree requirements | Determine whether or not referees can be secured or if they should be used | Potentially self officiate for all but final round | Operations | TBD | TBD | TBD | TBD
5.3 | Recruit Volunteers | Recruit Volunteers to assist with check-in, court assignments, etc. |  |  | TBD | TBD | TBD | TBD

## Committee
Committees Overview |  | Operations |  | Creative |  | Sponsorship
Name | Description | Name | Role | Name | Role | Name | Role
Operations | Responsible for defining tournament structure, registration fees, rules, etc. This committee is the foundation for a well-run event | Kyle Smith | Lead | Maddie Gipson | Lead | Randy Fontanez | Lead
Marketing | Responsible for creative marketing of event, decorations, sponsorship ideas, etc. This committee is the foundation for a FUN event. | Brent Terry |  | Berkley Terry |  | Yiannis Neocleous
Sponsorship | Responsible for partnering with the community to identify sponsors for the event. This committee the foundation for fundrasing. | Randy Fontanez |  | Brent Terry |  | Brent Terry

## Sponsor List
Sponsors |  |  | Tiers
Company | Level | Amount | Level |  | Gold | Silver | Bronze
NightHawk | Gold | 1000 | Amount | Description | 1000 | 500 | 250
RRB Partners | Gold | 1000 | Championship Court Sponsor | Company logo displayed on court surface and surrounding area | x
Neos & Co | Silver | 500 | Individual Court Sponsor | Company logo displayed on court surface and net |  | x
I A.M. | Silver | 500 | Player Registrations | Number of player registrations permitted (1 team is comprised of 2 players.) | 4 | 2
Nona Wealth Advisors | Bronze | 250 | Display company banner at podium wall | Company logo will be displayed on a banner behind podium for awards | x | x | x
Allstate | Bronze | 250 | Prominent logo on t-shirt | Prominent on t-shirt | x
Eat Drink Orlando | Bronze | 250 | Logo on t-shirt | Logo displayed on t-shirt |  | x | x
Simplified Mortgage | Bronze | 250 | Listed on website, banner, social media, etc. | Logo displayed on supoprted marketing materials | x | x | x
Bolay | Bronze | Share it Night
Diadem Sports | Product | Product
Power Pickleball | Product | Software
Total |  | 4000

## Brack Age Groups
Age Brackets
Ages | Notes
u50 | The age of the youngest player is used to determine the age group bracket.
50+

## Sign Ups
Sign Ups
Brent | Terry |  | 40 | Placeholder | RRB
Berkley | Terry |  | 40 | Placeholder | RRB
Austin | Ulcak |  | 60 | Placeholder | RRB
Cylie | Ulcak |  | 60 | Placeholder | RRB
Brian | Stenstrud | Partner hasn't signed up yet | 40 | Placeholder | NightHawk
Jennifer | Preston |  | 60 | Placeholder | NightHawk
John | Preston |  | 60 | Placeholder | NightHawk
Christine | Payne |  | 60 | Placeholder | NightHawk
Emily | Katz |  | 60 | Placeholder | Neos & Co
Denise | Rizzo |  | 60 | Placeholder | Neos & Co
Lisa | Miller |  | 60 | Placeholder | I Am
|  | 600 |  | Placeholder | I Am

## Budget
Costs |  | Sponsors |  | Participants |  | Total
Item | Cost | Company | Cost | Number | Total | Item | Cost
Venue Rental | 1200 | TBD | 0 | Price per team | 45 | Costs | 2200
T-Shirts | 1000 |  |  | Sign Ups | 100 | Sponsors | 4000
Referees | 0 |  |  | Total | 4500 | Sign Ups ($) | 4500
Flyers | 85 |  |  |  |  | Net | 6300